## Burn Down
Priority | JIRA | Description | Owner | Deliverable | Bug ID | Postponed | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
| YESSAFE-3896 | 客户端更新并解析照片包, 用户可以在线跟新头像（IOS） | Xie Peng |  |  |  | 1: 12
| YESSAFE-3899 | API 接口认证，在公网上外部应用请求API的时候需要认证, 客户端修改(IOS) | Xie Peng |  |  |  | 1: 16
| YESSAFE-3901 | 登录时设定大于输入错误次数时，自动清除数据，重新设置登录信息和用户信息(IOS)，默认最大5次错误，输错三次等5分钟. 第四次错误，再等5分钟，第5次错，清除数据 | Xie Peng |  |  |  | 1: 6
| YESSAFE-3905 | 在卡片列表中，常用卡增加显示特殊标识方便用户查找（ios） | Xie Peng |  |  |  | 1: 6
| YESSAFE-3904 | UI设计上，新增欢迎页面动画。(ios) | Xie Peng |  |  |  | 1: 6
| YESSAFE-4396 | iOS-卡主页面调整 | Xie Peng |  |  |  | 1: 6
| YESSAFE-4397 | iOS- 解锁后直接进入到"个人卡片"页面 | Xie Peng |  |  |  | 1: 6
| YESSAFE-4398 | iOS - translation question "Confirm" change to "OK" | Xie Peng |  |  |  | 1: 2

## Resource Allocation
|  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Utilization | Resource | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
100% | Tan Yong Ge | 1: 0
100% | Liu Zhi Shan | 1: 0
100% | Zhuang JianNing | 1: 0
100% | Xie Peng | 1: 60
100% | Zhang JiaQun | 1: 0
100% | Yang Feiwei | 1: 0
100% | Su ZiHang | 1: 0
100% | LiYang | 1: 0
xxx
100% | Resource#10 | 1: 0
| Hours Remaining | 1: 60

## Actual Allocation
|  | Over/(Under) | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Resource | Max Hours | Commited | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Tan Yong Ge | #VALUE! |  | 1: 0
Liu Zhi Shan | #VALUE! |  | 1: 0
Zhuang JianNing | #VALUE! |  | 1: 0
Xie Peng | #VALUE! |  | 1: 60
Zhang JiaQun | #VALUE! |  | 1: 0
Yang Feiwei | #VALUE! |  | 1: 0
Su ZiHang | #VALUE! |  | 1: 0
LiYang | #VALUE! |  | 1: 0
xxx | #VALUE! |  | 1: 0
Resource#10 | #VALUE! |  | 1: 0
Hours Remaining |  |  | 1: #VALUE!

## Sprint Information
Sprint Length | 10
Work Hours in Day | 6 | <- Leave at 1 if work estimates for tasks on "Burn Down" worksheet are in days
Start date | 2015-01-26
|  | Dev Start | Dev Complete | SIT Complete | UAT Complete
|  | 2015-03-23 | 2015-04-03 | 2015-04-07 | 2015-04-15
Do not modify anything below this line!!!!
Number Tasks | 8
Desired Trend | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Remaining Avail | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Postponed | Yes | No
Individual Base | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Release Sprint | #VALUE! | Release at End of Sprint ?
Upper Formula | #VALUE! | #VALUE!
Lower Formula | #VALUE! | #VALUE!
Upper Trend
Lower Trend
Chart Name | #VALUE!

## Release Burn Down
Sprint | Progress | Scope Change
1 |  | 0
2 |  | 0